## Annexure-I(Combinedupgradation)
Annexure-I
Combined Status of Upgradation of sites under Development of Water Resources Informtion System for the Month of | [9 empty] | 2015-06-01
Name of Scheme: Hydrological observations, including snow hydrology, water quality and monitoring of glacial lakes
Name of Organization : NTBO Gandhinagar.
A | Mahi Division Gandhinagar.
Sl .No. | Site Upgraded | [5 empty] | Type of site |  |  | Instrument aquired | No of W/C persons posted at present | Remarks
| Site upgraded | Name of river | Basin | District | state | Upgraded with effect from | Earlier | Upgraded | Further upgradation required |  | SWA
No site is to be upgraded in DWRIS plan scheme.
B | Tapi Div Surat
Sl .No. | Site Upgraded | [5 empty] | Type of site |  |  | Instrument aquired | No of W/C persons posted at present | Remarks
| Site upgraded | Name of river | Basin | District | state | Upgraded with effect from | Earlier | Upgraded | Further upgradation required |  | SWA
1 | Bharuch | Narmada | Narmada | Bharuch | Gujarat | 06.02.2014 | G | GD | No | Current Meter, Counter,Gauge plates ,Stevenson screen , Thermometer, OB Engine, FRP Boat supplied. | 3 | Work completed but additional man power required
2 | Ghala | Tapi | Tapi | Surat | Gujarat | 30.01.2014 | G | GD | No | Current Meter, Counter,Gauge plates ,Stevenson screen , Thermometer, OB Engine, FRP Boat supplied. | 1 | Work completed but additional man power required
3 | Daman | Damanganga | Damanganga | UT | D&N | 10.03.2014 | G | GD | No | Current Meter, Counter,Gauge plates ,Stevenson screen , Thermometer, Bridge outfit supplied. | 1 | Work completed but additional man power required
4 | Dedtalai | Tapi | Tapi | Khanwa | Madhya Pradesh | 06.02.2014 | G | GD | No | Current Meter, Counter,Gauge plates ,Stevenson screen , Thermometer, Bridge outfit supplied. | 1 | Work completed but additional man power required
5 | Bhusawal | Tapi | Tapi | Jalgaon | Maharashtra | 06.03.2014 | G | GD | No | Current Meter, Counter,Gauge plates ,Stevenson screen , Thermometer, Bridge outfit supplied. | 2 | Work completed but additional man power required
6 | Dahigaon | Girna | Tapi | Jalgaon | Maharashtra | 11.03.2014 | G | GD | No | Current Meter, Counter,Gauge plates ,Stevenson screen , Thermometer, Bridge outfit supplied. | 2 | Work completed but additional man power required
7 | Morane | Panjara | Tapi | Dhule | Maharashtra | 17.03.2014 | G | GD | No | Current Meter, Counter,Gauge plates ,Stevenson screen , Thermometer, Bridge outfit supplied. | 2 | Work completed but additional man power required

## Annex-I_Tapi
Annexure-I
Status of Upgradation of sites under Development of Water Resources Information System for the Month of June 2015.
Name of Scheme: Hydrological observations, including snow hydrology, water quality and monitoring of glacial lakes.
Name of Organization : Tapi Division, CWC, Surat.
Sr. No. | Site upgraded | Name of River | Basin | District | State | W.e.f. (Date) | Type of Site |  | Further upgradation required | Instrument acquired | No. of W/C staff posted at present | Remarks
[7 empty] | Earlier | Upgraded
1 | Bharuch | Narmada | Narmada | Bharuch | Gujarat | 06.02.2014 | G | GD | No | Current Meter, Counter,Gauge plates ,Stevenson screen , Thermometer, OB Engine, FRP Boat supplied. | 3 | Work completed but additional man power required
2 | Ghala | Tapi | Tapi | Surat | Gujarat | 30.01.2014 | G | GD | No | Current Meter, Counter,Gauge plates ,Stevenson screen , Thermometer, OB Engine, FRP Boat supplied. | 1 | Work completed but additional man power required
3 | Daman | Damanganga | Damanganga | UT | D&N | 10.03.2014 | G | GD | No | Current Meter, Counter,Gauge plates ,Stevenson screen , Thermometer, Bridge outfit supplied. | 1 | Work completed but additional man power required
4 | Dedtalai | Tapi | Tapi | Khanwa | Madhya Pradesh | 06.02.2014 | G | GD | No | Current Meter, Counter,Gauge plates ,Stevenson screen , Thermometer, Bridge outfit supplied. | 1 | Work completed but additional man power required
5 | Bhusawal | Tapi | Tapi | Jalgaon | Maharashtra | 06.03.2014 | G | GD | No | Current Meter, Counter,Gauge plates ,Stevenson screen , Thermometer, Bridge outfit supplied. | 2 | Work completed but additional man power required
6 | Dahigaon | Girna | Tapi | Jalgaon | Maharashtra | 11.03.2014 | G | GD | No | Current Meter, Counter,Gauge plates ,Stevenson screen , Thermometer, Bridge outfit supplied. | 2 | Work completed but additional man power required
7 | Morane | Panjara | Tapi | Dhule | Maharashtra | 17.03.2014 | G | GD | No | Current Meter, Counter,Gauge plates ,Stevenson screen , Thermometer, Bridge outfit supplied. | 2 | Work completed but additional man power required
7 | Morane | Panjara | Tapi | Dhule | Maharashtra | 17.03.2014 | G | GD | No | Current Meter, Counter,Gauge plates ,Stevenson screen , Thermometer, Bridge outfit supplied. | 2 | Work completed but additional man power required

## Annex_I_Mahi
Annexure-I
Status of Upgradation of sites under Development of Water Resources Information System for the Month of June 2015.
Name of Scheme: Hydrological observations, including snow hydrology, water quality and monitoring of glacial lakes
Name of Organization :NTBO Gandhinagar Mahi Division
Sr. No. | Site upgraded | Name of River | Basin | District | State | W.e.f. (Date) | Type of Site |  | Further upgradation required | Instrument acquired | No. of W/C staff posted at present | Remarks
[7 empty] | Earlier | Upgraded
No site is to be upgraded in DWRIS plan scheme.

## Annexure-II (combined)
Combined Status of Opening of new sites under Development of Water Resources Informtion System for the Month of | [11 empty] | Annexure-II
Name of Scheme: Hydrological observations, including snow hydrology, water quality and monitoring of glacial lakes
| Name of Organization : NTBO Gandhinagar. | [10 empty] | 2015-06-01
A | Mahi Division Gandhinagar.
SN | Name of Site | Name of River | Basin | District | State | Type of Site | Date of Opening | Land Status | satatus of Equipment | Status of tender process | Status of Civil work | Remark
1 | Borwa | Mahi | Mahi | Ratlam | MP | G | To be finalised | Taken up with State Government | Auto Level , ORG & Wind Wane, Current meter, Stop watch, Digital counter, SRRG, office furniture has been procured | SO for office furniture has been placed . | Civil work to be taken up after land alocation | As data for sites 2,3 & 4 will be used for inflow forecasting reconnaissance survey for suitable location in progress. Earlier selected section not found suitable after detailed survey.So new recoinnasaicce survey has been carrioed out and selected new locations are site 1. Sohargpura on river Erav.2 khandiovari site on river Som & 3 Amarpura on river Tidi.
2 | Sohagpura | Mahi | Erav | Pratapgarh | Rajasthan | GD |  | Exact locations are under finalisation & land issue to be taken up with State Government.
3 | Khandiovari | Mahi | Som River | Udaipur | Rajasthan | G | [6 empty] | °
4 | Amarpura | Mahi |  | Udaipur | Rajasthan | GD
5 | Una | Machundri | Machundri | Junagarh | Gujarat | GD | Temporarly opened on 26.7.14 | Superintending Engineer, Rajkot Irrigation Circle, Rajkot alloted a plot of land size 14mx26m =364 sqm at site Una for a period of 99 years on lease basis from the date of commencement of lease agreement . The token rent for the above plot is Rs 20/- (Rupees twenty only) per annum and lumsum deposit of Rs 500/- (Rupees five hundred only). Signining of lease agreenment has been completed on 18.02.15. payment is also made. |  |  | After processing the lease agreement necessary step to be taken up for starting the civil works | G & D site at UNA temporary opened on 26/07/2014 under Sabarmati sub Division Ahmedabad and only Gauge observation started w.e.f 26/7/14.
B | Tapi Div, Surat
Sl . No. | Name of site | Name of river | Basin | District | state | Type of site | date of opening | Land status | status of equipment | status of tender process | status of civil works | remarks
1 | Kathore | Tapi | Tapi | Surat | Gujarat | G | Temporarily opened by installing temporary gauge posts on 30.09.2014 .GTS connection , site survey and X-sections have been taken. | Irrigation department, Govt. of Gujarat alloted land on lease, land has been acquired and yearly lease payment has been made. | Instruements identified . Estimates prepared. NIQ done for autolevel, rain guage and Stevenson screen. Stevenson screen and Autolevel received. | Under process | 1. Estimate prepared for RCC Gauge posts.. Tender invited and work completed. 2.Drawing and Estimate prepared for site office building. | Staff is required after opening of site.
2 | Prakasha | Gomai | Tapi | Nandurbar | Maharashtra | GD | Temporarily opened by installing temporary gauge posts on 30.09.2014. GTS connection, site survey and X-sections have been taken. | Damarkheda Gram Panchayat is agreed to provide land for site office and application has been given. Case is under process. | Instruements identified . Estimates prepared. NIQ done for autolevel, bridge outfit, rain guage, stevenson screen. Autolevel, stevenson screen, current meter and Bridge outfit received | Under process | 1. Estimate prepared for RCC Gauge posts Tender invited and work in progress . 2.Estimate for civil works under preparation. | Staff is required after opening of site.
3 | Lohara | Mun | Tapi | Akola | Maharashtra | GD | Temporarily opened by installing temporary gauge posts on 28.07.2014..GTS connection, site srvey and X-sections have been taken. | Govt land is not available .Private accomadation for site office is taken on rent from Ist Aug.2014 | Instruements identified . Estimates prepared. NIQ done for autolevel, bridge outfit, rain guage, stevenson screen. .Autolevel, stevenson screen, current meter & Bridge outfit received | Under process | 1. Estimate prepared for RCC Gauge posts . Tender invited and work completed. 2.Estimate for civil works under preparation. | Staff is required after opening of site.
4 | Uchhal | Tapi | Tapi | Tapi | Gujarat | G | Land for opening of site in search. | Land for opening of site office in search. | Instruements has been identified . Estimates under preparation. | Under process | Estimate under preparation for Gauge posts.and civil works. | Staff is required after opening of site.
5 | Ver | Ver | Tapi | Tapi | Gujarat | GD | Land for opening of site in search. | Land for opening of site office in search. | Instruements has been identified . Estimates under preparation. | Under process | Estimate under preparation for Gauge posts.and civil works. | Staff is required after opening of site.
6 | Sindhkheda | Buray | Tapi | Dhule | Maharashtra | GD | Land for opening of site in search. | Land for opening of site office in search. | Instruements has been identified . Estimates under preparation. | Under process | Estimate under preparation for Gauge posts.and civil works. | Staff is required after opening of site.
7 | Taloda | Manyad | Tapi | Nandurbar | Maharashtra | GD | Land for opening of site in search. | Land for opening of site office in search. | Instruements has been identified . Estimates under preparation. | Under process | Estimate under preparation for Gauge posts.and civil works. | Staff is required after opening of site.
8 | Sirpur | Arunavati | Tapi | Dhule | Maharahtra | GD | Land for opening of site in search. | Land for opening of site office in search. | Instruements has been identified . Estimates under preparation. | Under process | Estimate under preparation for Gauge posts.and civil works. | Staff is required after opening of site.
9 | Akola | Morna | Tapi | Akola | Maharashtra | G | Land for opening of site in search. | Land for opening of site office in search. | Instruements has been identified . Estimates under preparation. | Under process | Estimate under preparation for Gauge posts.and civil works. | Staff is required after opening of site.
10 | Kurankheda | Katepurna | Tapi | Akola | Maharashtra | GD | Land for opening of site in search. | Land for opening of site office in search. | Instruements has been identified . Estimates under preparation. | Under process | Estimate under preparation for Gauge posts.and civil works. | Staff is required after opening of site.
11 | Pinakwadi | Shanur | Tapi | Akola | Maharashtra | G | Land for opening of site in search. | Land for opening of site office in search. | Instruements has been identified . Estimates under preparation. | Under process | Estimate under preparation for Gauge posts.and civil works. | Staff is required after opening of site.
12 | Vankhed | Van | Tapi | Buldhana | Maharashtra | GD | Land for opening of site in search. | Land for opening of site office in search. | Instruements has been identified . Estimates under preparation. | Under process | Estimate under preparation for Gauge posts.and civil works. | Staff is required after opening of site.
0

## Annex_II_Tapi
Status of Opening of new sites under Development of Water Resources Information System for the Month of June 2015 | [10 empty] | Annexure-II
Name of Scheme: Hydrological observations, including snow hydrology, water quality and monitoring of glacial lakes
Name of Organization : NTBO, Tapi Division, CWC, Surat
Sr. No. | Name of site | Name of River | Basin | District | State | Type of Site | Date of Opening | Land Status | Status of Equipment | Status of tender process | Status of civil work | Remark
1 | Kathore | Tapi | Tapi | Surat | Gujarat | G | Temporarily opened by installing temporary gauge posts on 30.09.2014 .GTS connection , site survey and X-sections have been taken. | Irrigation department, Govt. of Gujarat alloted land on lease, land has been acquired and yearly lease payment has been made. | Instruements identified . Estimates prepared. NIQ done for autolevel, rain guage and Stevenson screen. Stevenson screen and Autolevel received. | Under process | 1. Estimate prepared for RCC Gauge posts.. Tender invited and work completed. 2.Drawing and Estimate prepared for site office building. | Staff is required after opening of site.
2 | Prakasha | Gomai | Tapi | Nandurbar | Maharashtra | GD | Temporarily opened by installing temporary gauge posts on 30.09.2014. GTS connection, site survey and X-sections have been taken. | Damarkheda Gram Panchayat is agreed to provide land for site office and application has been given. Case is under process. | Instruements identified . Estimates prepared. NIQ done for autolevel, bridge outfit, rain guage, stevenson screen. Autolevel, stevenson screen, current meter and Bridge outfit received | Under process | 1. Estimate prepared for RCC Gauge posts Tender invited and work in progress . 2.Estimate for civil works under preparation. | Staff is required after opening of site.
3 | Lohara | Mun | Tapi | Akola | Maharashtra | GD | Temporarily opened by installing temporary gauge posts on 28.07.2014..GTS connection, site srvey and X-sections have been taken. | Govt land is not available .Private accomadation for site office is taken on rent from Ist Aug.2014 | Instruements identified . Estimates prepared. NIQ done for autolevel, bridge outfit, rain guage, stevenson screen. .Autolevel, stevenson screen, current meter & Bridge outfit received | Under process | 1. Estimate prepared for RCC Gauge posts . Tender invited and work completed. 2.Estimate for civil works under preparation. | Staff is required after opening of site.
4 | Uchhal | Tapi | Tapi | Tapi | Gujarat | G | Land for opening of site in search. | Land for opening of site office in search. | Instruements has been identified . Estimates under preparation. | Under process | Estimate under preparation for Gauge posts.and civil works. | Staff is required after opening of site.
5 | Ver | Ver | Tapi | Tapi | Gujarat | GD | Land for opening of site in search. | Land for opening of site office in search. | Instruements has been identified . Estimates under preparation. | Under process | Estimate under preparation for Gauge posts.and civil works. | Staff is required after opening of site.
6 | Sindhkheda | Buray | Tapi | Dhule | Maharashtra | GD | Land for opening of site in search. | Land for opening of site office in search. | Instruements has been identified . Estimates under preparation. | Under process | Estimate under preparation for Gauge posts.and civil works. | Staff is required after opening of site.
7 | Taloda | Manyad | Tapi | Nandurbar | Maharashtra | GD | Land for opening of site in search. | Land for opening of site office in search. | Instruements has been identified . Estimates under preparation. | Under process | Estimate under preparation for Gauge posts.and civil works. | Staff is required after opening of site.
8 | Sirpur | Arunavati | Tapi | Dhule | Maharahtra | GD | Land for opening of site in search. | Land for opening of site office in search. | Instruements has been identified . Estimates under preparation. | Under process | Estimate under preparation for Gauge posts.and civil works. | Staff is required after opening of site.
9 | Akola | Morna | Tapi | Akola | Maharashtra | G | Land for opening of site in search. | Land for opening of site office in search. | Instruements has been identified . Estimates under preparation. | Under process | Estimate under preparation for Gauge posts.and civil works. | Staff is required after opening of site.
10 | Kurankheda | Katepurna | Tapi | Akola | Maharashtra | GD | Land for opening of site in search. | Land for opening of site office in search. | Instruements has been identified . Estimates under preparation. | Under process | Estimate under preparation for Gauge posts.and civil works. | Staff is required after opening of site.
11 | Pinakwadi | Shanur | Tapi | Akola | Maharashtra | G | Land for opening of site in search. | Land for opening of site office in search. | Instruements has been identified . Estimates under preparation. | Under process | Estimate under preparation for Gauge posts.and civil works. | Staff is required after opening of site.
12 | Vankhed | Van | Tapi | Buldhana | Maharashtra | GD | Land for opening of site in search. | Land for opening of site office in search. | Instruements has been identified . Estimates under preparation. | Under process | Estimate under preparation for Gauge posts.and civil works. | Staff is required after opening of site.

## Annex_II_Mahi
5 | Una | Machundri | Machundri | Junagarh | Gujarat | GD | Temporary open on 26.7.14 | Superintending Engineer, Rajkot Irrigation Circle, Rajkot alloted a plot of land size 14mx26m =364 sqm at site Una for a period of 99 years on lease basis from the date of commencement of lease agreement . The token rent for the above plot is Rs 20/- (Rupees twenty only) per annum and lumsum deposit of Rs 500/- (Rupees five hundred only). Signining of lease agreenment has been completed on 18.02.15. payment is also made. |  |  |  | G & D site at UNA temporary opened on 26/07/2014 under Sabarmati sub Division Ahmedabad and only Gauge observation started w.e.f 26/7/14.
Name of Scheme: Hydrological observations, including snow hydrology, water quality and monitoring of glacial lakes
Name of Organization :NTBO Gandhinagar Mahi DIivision
Sr. No. | Name of site | Basin | Name of River | District | State | Type of Site | Date of Opening | Land Status | Status of Equipment | Status of tender process | Status of civil work | Remark
1 | Borwa | Mahi | Mahi | Ratlam | MP | G | To be finalised | Taken up with State Government | Auto Level , ORG & Wind Wane, Current meter, Stop watch, Digital counter, SRRG, office furniture has been procured | SO for office furniture has been placed . | Civil work to be taken up after land alocation | As data for sites 2,3 & 4 will be used for inflow forecasting reconnaissance survey for suitable location in progress. Earlier selected section not found suitable after detailed survey.So new recoinnasaicce survey has been carrioed out and selected new locations are site 1. Sohargpura on river Erav.2 khandiovari site on river Som & 3 Amarpura on river Tidi.
2 | Sohagpura | Mahi | Erav | Pratapgarh | Rajasthan | GD |  | Exact locations are under finalisation & land issue to be taken up with State Government.
3 | Khandiovari | Mahi | Som River | Udaipur | Rajasthan | G
4 | Amarpura | Mahi | Tidi River | Udaipur | Rajasthan | GD
5 | Una | Machundri | Machundri | Junagarh | Gujarat | GD | Temporarly opened on 26.7.14 | Superintending Engineer, Rajkot Irrigation Circle, Rajkot alloted a plot of land size 14mx26m =364 sqm at site Una for a period of 99 years on lease basis from the date of commencement of lease agreement . The token rent for the above plot is Rs 20/- (Rupees twenty only) per annum and lumsum deposit of Rs 500/- (Rupees five hundred only). Signining of lease agreenment has been completed on 18.02.15. payment is also made. |  |  | After processing the lease agreement necessary step to be taken up for starting the civil works | G & D site at UNA temporary opened on 26/07/2014 under Sabarmati sub Division Ahmedabad and only Gauge observation started w.e.f 26/7/14.
Executive Engineer

## combined part A
WORK PLAN OF MOWR FOR THE F.Y. 2015-16
Development of Water Resources Information System (DWRIS) Plan Scheme
Progress of Upgradation and continuation of Hydrological Observation including Snow Hydrology and Monitoring of Glacial Lakes in existing network under CWC in F.Y 2015-16
For the Month of June 2015 |  |  |  | Combined status of Mahi Division and Tapi Division under NTBO Gandhinagar | [12 empty] | Amount in Crore |  |  |  | Amount in Crore
S.No | Activity | Financial Progress (INR in Crore) | Financial Progress | [15 empty] | CUMMULATIVE | Physical Target | Physical Ach. | Remarks Tapi division Surat | Remarks Mahi division Gandhinagar
|  |  | Q1 |  |  |  | Q2 |  |  |  | Q3 |  |  |  | Q4
|  |  | April | May | June | Total- Q1 | July | Aug | Sep | Total- Q2 | Oct | Nov | Dec | Total- Q3 | Jan | Feb | Mar | Total- Q4
1 | Part-A: Upgradation and continuation of Hydrological Observation including Snow Hydrology and Monitoring of Glacial Lakes in existing network under Central Water Commission. | Target Exp. | #VALUE! | #VALUE! | 0.1424 | 0.96894 | #VALUE! | #VALUE! | #VALUE! | 1.0658 | #VALUE! | 0.36053 | 0.71315 | 1.2112 | #VALUE! | #VALUE! | #VALUE! | 1.5988 | 4.8447 | #REF! | #REF!
|  | Actual Exp. | 0.1692 | 0.1211 | 0.1739 | 0.4642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4642 | #REF! | 0
A. | Regular Establishment | Target Exp. | 0.0104 | 0.03096 | 0.06192 | 0.1032 | 0.011352 | 0.034056 | 0.068112 | 0.11352 | 0.0129 | 0.0387 | 0.0774 | 0.129 | 0.04644 | 0.04644 | 0.0774 | 0.17028 | 0.516 | #REF! | 0
|  | Actual Exp. | 0.0367 | 0.022 | 0.0353 | 0.094 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.094 | #REF! | #REF!
B. | Work Charged Establishment | Target Exp. | 0.0578 | 0.04101 | 0.04682 | 0.1367 | 0.015037 | 0.045111 | 0.090222 | 0.15037 | 0.017087 | 0.051263 | 0.10253 | 0.17087 | 0.061515 | 0.061515 | 0.10253 | 0.22556 | 0.6835 | #REF! | 0 | #REF! | #REF!
|  | Actual Exp. | 0.1014 | 0.0476 | 0.0493 | 0.1983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1983 | #REF! | #REF!
C. | Outsourcing of JRF | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | 0
|  | Actual Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF!
D. | Minor Works
a) | Construction of Site office including land cost for site | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Actual Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
b) | Upgradation of existing Sites | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Actual Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
c) | R&M of existing Sites | Target Exp. | 0.0022 | 0.01758 | 0.03516 | 0.0586 | 0.006446 | 0.019338 | 0.038676 | 0.06446 | 0.007325 | 0.021975 | 0.04395 | 0.07325 | 0.02637 | 0.02637 | 0.04395 | 0.09669 | 0.293
|  | Actual Exp. | 0.005 | 0.038 | 0.0604 | 0.1034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1034
d) | AMC of the equipment, computer, printer & photocopier etc. | Target Exp. | 4e-05 | 0.18012 | 0.36024 | 0.6004 | 0.066044 | 0.19813 | 0.39626 | 0.66044 | 0.07505 | 0.22515 | 0.4503 | 0.7505 | 0.27018 | 0.27018 | 0.4503 | 0.99066 | 3.002
|  | Actual Exp. | 0.0005 | 0.0012 | 0.0012 | 0.0029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0029
e) | R&M of Data Centre | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Actual Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
f) | Out sourcing of DEO, MTS and Watch & Ward services od Sub division | Target Exp. | 0.001 | 0.002592 | 0.005184 | 0.00864 | 0.0009504 | 0.0028512 | 0.0057024 | 0.009504 | 0.00108 | 0.00324 | 0.00648 | 0.0108 | 0.003888 | 0.003888 | 0.00648 | 0.014256 | 0.0432
|  | Actual Exp. | 0.0022 | 0.0022 | 0 | 0.0044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0044
g) | Snow Hydrology and Glacial Studies | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Actual Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
h) | Hiring of Inspection Vehicles | Target Exp. | 0.001 | 0.00288 | 0.00576 | 0.0096 | 0.001056 | 0.003168 | 0.006336 | 0.01056 | 0.0012 | 0.0036 | 0.0072 | 0.012 | 0.00432 | 0.00432 | 0.0072 | 0.01584 | 0.048
|  | Actual Exp. | 0.0086 | 0.0064 | 0.0027 | 0.0177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0177
D | Motor Vehicle | Target Exp. | #VALUE! | #VALUE! | #VALUE! | 0.0198 | #VALUE! | #VALUE! | #VALUE! | 0.02178 | #VALUE! | 0.0046 | 0.0013 | 0.02475 | #VALUE! | #VALUE! | #VALUE! | 0.03267 | 0.099
|  | Actual Exp. | 0.0148 | 0.0037 | 0.025 | 0.0435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0435
i | R&M of Motor Vehicle including salary of MV Driver |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0.0046 | 0.0013 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
ii | Procurement of Inspection Vehicle |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E | Machinery & Equipment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
a) | Purchase of High value equipment ( > 5 Lakh) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
b) | Purchase of Low value equipment (< 5 Lakh) |  | 0.0028 | 0.0096 | 0.0192 | 0.032 | 0.00352 | 0.01056 | 0.02112 | 0.0352 | 0.004 | 0.012 | 0.024 | 0.04 | 0.0144 | 0.0144 | 0.024 | 0.0528 | 0.16
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Part_A Tapi
WORK PLAN OF CWC FOR THE F.Y. 2015-16
Development of Water Resources Information System (DWRIS) Plan Scheme
Progress of Upgradation and continuation of Hydrological Observation including Snow Hydrology and Monitoring of Glacial Lakes in existing network under Tapi division, CWC, Surat.
For the Month of June 2015 | [5 empty] | Tapi division | [11 empty] | Amount in crore
S.No | Activity | Financial Progress (INR in Crore) | Physical Progress | [15 empty] | CUMMULATIVE | Physical Target | Physical Ach.
|  |  | Q1 |  |  |  | Q2 |  |  |  | Q3 |  |  |  | Q4
|  |  | April | May | June | Total- Q1 | July | Aug | Sep | Total- Q2 | Oct | Nov | Dec | Total- Q3 | Jan | Feb | Mar | Total- Q4
1 | Part-A: Upgradation and continuation of Hydrological Observation including Snow Hydrology and Monitoring of Glacial Lakes in existing network under Central Water Commission. | Target Exp. | 0.025 | 0.24572 | 0.50904 | 0.82654 | 0.088741 | 0.26622 | 0.53245 | 0.90919 | 0.10084 | 0.30253 | 0.60506 | 1.0332 | 0.36303 | 0.36303 | 0.60506 | 1.3638 | 4.1327
|  | Actual Exp. | 0.0856 | 0.0793 | 0.0843 | 0.2492 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2492
A. | Regular Establishment | Target Exp. | 0.008 | 0.02376 | 0.04752 | 0.0792 | 0.008712 | 0.026136 | 0.052272 | 0.08712 | 0.0099 | 0.0297 | 0.0594 | 0.099 | 0.03564 | 0.03564 | 0.0594 | 0.13068 | 0.396 | 5
|  | Actual Exp. | 0.036 | 0.0202 | 0.0281 | 0.0843 | [12 empty] | 0.0843
B. | Work Charged Establishment | Target Exp. | 0.005 | 0.01461 | 0.02922 | 0.0487 | 0.005357 | 0.016071 | 0.032142 | 0.05357 | 0.0060875 | 0.018263 | 0.036525 | 0.060875 | 0.021915 | 0.021915 | 0.036525 | 0.080355 | 0.2435 | 7
|  | Actual Exp. | 0.0296 | 0.0141 | 0.0156 | 0.0593 | [12 empty] | 0.0593
C. | Minor Works
a) | Construction of Site office including land cost for site | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Actual Exp. | 0 | 0 | 0 | 0
b) | Upgradation of existing Sites | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Actual Exp. | 0 | 0 | 0 | 0
c) | R&M of existing Sites | Target Exp. | 0 | 0.01098 | 0.02196 | 0.0366 | 0.004026 | 0.012078 | 0.024156 | 0.04026 | 0.004575 | 0.013725 | 0.02745 | 0.04575 | 0.01647 | 0.01647 | 0.02745 | 0.06039 | 0.183 | 37
|  | Actual Exp. | 0.0012 | 0.0315 | 0.0129 | 0.0456 | [12 empty] | 0.0456
d) | AMC of the equipment, computer, printer & photocopier etc. | Target Exp. | 0 | 0.18 | 0.36 | 0.6 | 0.066 | 0.198 | 0.396 | 0.66 | 0.075 | 0.225 | 0.45 | 0.75 | 0.27 | 0.27 | 0.45 | 0.99 | 3
|  | Actual Exp. | 0.0005 | 0.0012 | 0 | 0.0017 | [12 empty] | 0.0017
e) | R&M of Data Centre | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
|  | Actual Exp. | 0 | 0 | 0 | 0
f) | Out sourcing of DEO, MTS and Watch & Ward services | Target Exp. | 0.001 | 0.002592 | 0.005184 | 0.00864 | 0.0009504 | 0.0028512 | 0.0057024 | 0.009504 | 0.00108 | 0.00324 | 0.00648 | 0.0108 | 0.003888 | 0.003888 | 0.00648 | 0.014256 | 0.0432 | 2 | 0
|  | Actual Exp. | 0.0022 | 0.0022 | 0 | 0.0044 | [12 empty] | 0.0044
g) | Snow Hydrology and Glacial Studies | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Actual Exp. | 0 | 0 | 0 | 0
h) | Hiring of Inspection Vehicles | Target Exp. | 0.001 | 0.00288 | 0.00576 | 0.0096 | 0.001056 | 0.003168 | 0.006336 | 0.01056 | 0.0012 | 0.0036 | 0.0072 | 0.012 | 0.00432 | 0.00432 | 0.0072 | 0.01584 | 0.048 | 1
|  | Actual Exp. | 0.0086 | 0.0064 | 0.0027 | 0.0177 | [12 empty] | 0.0177
D. | Motor Vehicle | Target Exp. | 0.008 | 0.0037 | 0.025 | 0.0198 | 0 | 0 | 0 | 0.02178 | 0 | 0 | 0 | 0.02475 | 0 | 0 | 0 | 0.03267 | 0.099 | 3
|  | Actual Exp. | 0.0075 | 0.0037 | 0.025 | 0.0362 | [12 empty] | 0.0362
i) | R&M of Motor Vehicle including salary of MV Driver |  | 0.0075 | 0.0037 | 0.025 | 0.0362 | [12 empty] | 0.0362 | 3
ii) | Procurement of Inspection Vehicle |  | 0 | 0 | 0 | 0 | [13 empty] | 0
E. | Machinery & Equipment
a) | Purchase of High value equipment ( > 5 Lakh) | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Actual Exp. | 0 | 0 | 0 | 0
b) | Purchase of Low value equipment (< 5 Lakh) | Target Exp. | 0.002 | 0.0072 | 0.0144 | 0.024 | 0.00264 | 0.00792 | 0.01584 | 0.0264 | 0.003 | 0.009 | 0.018 | 0.03 | 0.0108 | 0.0108 | 0.018 | 0.0396 | 0.12
|  | Actual Exp. | 0 | 0 | 0 | 0

## Part_A_Mahi
WORK PLAN OF CWC FOR THE F.Y. 2015-16
Development of Water Resources Information System (DWRIS) Plan Scheme
Progress of Upgradation and continuation of Hydrological Observation including Snow Hydrology and Monitoring of Glacial Lakes in existing network under CWC in F.Y 2015-16
For the Month of June 2015. |  |  |  | Mahi Division , |  | NTBO | [8 empty] | Gandhinagar | [5 empty] | Amount in Crore
S.No | Activity | Financial Progress (INR in Crore) | Physical Progress | [15 empty] | CUMMULATIVE | Physical Target | Physical Ach. | Remarks
|  |  | Q1 |  |  |  | Q2 |  |  |  | Q3 |  |  |  | Q4
|  |  | April | May | June | Total- Q1 | July | Aug | Sep | Total- Q2 | Oct | Nov | Dec | Total- Q3 | Jan | Feb | Mar | Total- Q4
1 | Part-A: Upgradation and continuation of Hydrological Observation including Snow Hydrology and Monitoring of Glacial Lakes in existing network under Central Water Commission. | Target Exp. | #VALUE! | #VALUE! | #VALUE! | 0.1424 | #VALUE! | #VALUE! | #VALUE! | 0.15664 | #VALUE! | 0.058 | 0.1081 | 0.178 | #VALUE! | #VALUE! | #VALUE! | 0.23496 | 0.712
|  | Actual Exp. | 0.0836 | 0.0418 | 0.0896 | 0.215 | 0 | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 | 0.215
A. | Regular Establishment | Target Exp. | 0.0024 | 0.0072 | 0.0144 | 0.024 | 0.00264 | 0.00792 | 0.01584 | 0.0264 | 0.003 | 0.009 | 0.018 | 0.03 | 0.0108 | 0.0108 | 0.018 | 0.0396 | 0.12 | 1 | Continuous work | 1 no Junior Engineer
|  | Actual Exp. | 0.0007 | 0.0018 | 0.0072 | 0.0097 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0.0097
B. | Work Charged Establishment | Target Exp. | 0.0528 | 0.0264 | 0.0176 | 0.088 | 0.00968 | 0.02904 | 0.05808 | 0.0968 | 0.011 | 0.033 | 0.066 | 0.11 | 0.0396 | 0.0396 | 0.066 | 0.1452 | 0.44 | 13 |  | Estt. of 13 WC Staff
|  | Actual Exp. | 0.0718 | 0.0335 | 0.0337 | 0.139 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0.139
C. | Minor Works
a) | Construction of Site office including land cost for site | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 Nos. to be completed on or before 31.03.2015
|  | Actual Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
b) | Upgradation of existing Sites | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Printing of year book, 1 no Water year Book, 1 no Sediment data Year Book & 1 no. Water quality year book
|  | Actual Exp. |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
c) | R&M of existing Sites | Target Exp. | 0.0022 | 0.0066 | 0.0132 | 0.022 | 0.00242 | 0.00726 | 0.01452 | 0.0242 | 0.00275 | 0.00825 | 0.0165 | 0.0275 | 0.0099 | 0.0099 | 0.0165 | 0.0363 | 0.11 | 38 | Continuous work | G, GD, GDQ & GDSQ
|  | Actual Exp. | 0.0038 | 0.0065 | 0.0475 | 0.0578 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0.0578
d) | AMC of the equipment, computer, printer & photocopier etc. | Target Exp. | 4e-05 | 0.00012 | 0.00024 | 0.0004 | 4.4e-05 | 0.000132 | 0.000264 | 0.00044 | 5e-05 | 0.00015 | 0.0003 | 0.0005 | 0.00018 | 0.00018 | 0.0003 | 0.00066 | 0.002 |  | Continuous work
|  | Actual Exp. |  |  | 0.0012 | 0.0012 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0.0012
e) | R&M of Data Centre | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  | Actual Exp. |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
f) | Out sourcing of DEO, MTS and Watch & Ward services od Sub division | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  | Actual Exp. |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
g) | Snow Hydrology and Glacial Studies | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Actual Exp. |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
h) | Hiring of Inspection Vehicles | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Actual Exp. |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
D. | Motor Vehicle | Target Exp. | #VALUE! | #VALUE! | #VALUE! | 0 | #VALUE! | #VALUE! | #VALUE! | 0 | #VALUE! | 0.0046 | 0.0013 | 0 | #VALUE! | #VALUE! | #VALUE! | 0 | 0
|  | Actual Exp. | 0.0073 |  |  | 0.0073 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0.0073
i) | R&M of Motor Vehicle including salary of MV Driver |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0.0046 | 0.0013 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0 | 0
ii) | Procurement of Inspection Vehicle |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E. | Machinery & Equipment
a) | Purchase of High value equipment ( > 5 Lakh) | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
|  | Actual Exp. |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
b) | Purchase of Low value equipment (< 5 Lakh) | Target Exp. | 0.0008 | 0.0024 | 0.0048 | 0.008 | 0.00088 | 0.00264 | 0.00528 | 0.0088 | 0.001 | 0.003 | 0.006 | 0.01 | 0.0036 | 0.0036 | 0.006 | 0.0132 | 0.04 |  |  | Misc Hydro-meteorological equip, survey equip, camp material & office furnitures etc.
|  | Actual Exp. |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  | 0

## combined partB
WORK PLAN OF MOWR FOR THE F.Y. 2015-16
Development of Water Resources Information System (DWRIS) Plan Scheme
Progress of Expansion of Hydrological Observation Network by opening new Hydrological Observation sites under CWC
For the Month of June 15 |  |  |  | Combined status of Mahi Division and Tapi Division under NTBO Gandhinagar | [13 empty] | Amount in Crore
S.No | Activity | Financial Progress (INR in Crore) | Finanacial Progress | [15 empty] | CUMMULATIVE | Physical Target | Physical Ach.
|  |  | Q1 |  |  |  | Q2 |  |  |  | Q3 |  |  |  | Q4
|  |  | April | May | June | Total- Q1 | July | Aug | Sep | Total- Q2 | Oct | Nov | Dec | Total- Q3 | Jan | Feb | Mar | Total- Q4
2 | Part-B: Expansion of Hydrological Observation Network by opening new Hydrological Observation sites under CWC | Target Exp. | 0.00016236 | 0.00048708 | 0.0020434 | 0.0017028 | 0.050817 | 0.15245 | 0.3049 | 0.50817 | 0.052366 | 0.1571 | 0.3142 | 0.52366 | 0.14213 | 0.13559 | 0.22391 | 0.50817 | 1.541 | #REF! | #REF!
|  | Actual Exp. | 0.1149 | 0.0128 | 0.0006 | 0.1283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1283 | #REF! | #REF!
A. | Regular Establishment | Target Exp. | 8.118e-05 | 0.00024354 | 0.00048708 | 0.0008118 | 0.001353 | 0.004059 | 0.008118 | 0.01353 | 0.001394 | 0.004182 | 0.008364 | 0.01394 | 0.00369 | 0.00369 | 0.00615 | 0.01353 | 0.041 | #REF! | #REF!
|  | Actual Exp. | 0.0004 | 0.0014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF!
B. | Work Charged Establishment | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF!
|  | Actual Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF!
C. | Minor Works |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
a) | Construction of Site office building including land cost for site | Target Exp. | 0 | 0 | 0.0005346 | 0.000891 | 0.027585 | 0.082755 | 0.16551 | 0.27585 | 0.02843 | 0.08529 | 0.17058 | 0.2843 | 0.07515 | 0.07515 | 0.12555 | 0.27585 | 0.837
|  | Actual Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
b) | Works for opening of New Site | Target Exp. | 0 | 0 | 0 | 0 | 0.002376 | 0.007128 | 0.014256 | 0.02376 | 0.002448 | 0.007344 | 0.014688 | 0.02448 | 0.010098 | 0.003564 | 0.003564 | 0.02376 | 0.072
|  | Actual Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
c) | R&M of Sites | Target Exp. | 0 | 0 | 0 | 0 | 0.001188 | 0.003564 | 0.007128 | 0.01188 | 0.001224 | 0.003672 | 0.007344 | 0.01224 | 0.00324 | 0.00324 | 0.0054 | 0.01188 | 0.036
|  | Actual Exp. | 0.0011 | 0.0014 | 0.0006 | 0.0031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
d) | Hiring of Watch & Ward Service | Target Exp. | 0 | 0 | 0 | 0 | 0.004752 | 0.014256 | 0.028512 | 0.04752 | 0.004896 | 0.014688 | 0.029376 | 0.04896 | 0.01296 | 0.01296 | 0.0216 | 0.04752 | 0.144
|  | Actual Exp. | 0.0166 | 0.01 | 0 | 0.0266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D | Motor Vehicle |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
i | Procurement of Inspection Vehicle | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Actual Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ii | R&M of Motor Vehicle including salary of Driver | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Actual Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
e) | Machinery & Equipment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Purchase of High value equipment ( > 5 Lakh) | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Actual Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Purchase of Low value equipment (< 5 Lakh) | Target Exp. | 0 | 0 | 0 | 0 | 0.013563 | 0.040689 | 0.081378 | 0.13563 | 0.013974 | 0.041922 | 0.083844 | 0.13974 | 0.03699 | 0.03699 | 0.06165 | 0.13563 | 0.411
|  | Actual Exp. | 0.0968 | 0 | 0 | 0.0968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0968

## PartB_Tapi
WORK PLAN OF MOWR FOR THE F.Y. 2015-16
Development of Water Resources Information System (DWRIS) Plan Scheme
Progress of Expansion of Hydrological Observation Network by opening new Hydrological Observation sites under Tapi division, CWC, Surat.
For the Month of June 2015 | [5 empty] | Tapi division | [11 empty] | Amount in crore
S.No | Activity | Financial Progress (INR in Crore) | Physical Progress | [15 empty] | CUMMULATIVE | Physical Target | Physical Ach.
|  |  | Q1 |  |  |  | Q2 |  |  |  | Q3 |  |  |  | Q4
|  |  | April | May | June | Total- Q1 | July | Aug | Sep | Total- Q2 | Oct | Nov | Dec | Total- Q3 | Jan | Feb | Mar | Total- Q4
2 | Part-B: Expansion of Hydrological Observation Network by opening new Hydrological Observation sites under CWC | Target Exp. | 0 | 0 | 0 | 0 | 0.045669 | 0.13701 | 0.27401 | 0.45669 | 0.047062 | 0.14119 | 0.28237 | 0.47062 | 0.12809 | 0.12155 | 0.20051 | 0.45669 | 1.385
|  | Actual Exp. | 0.0177 | 0.0114 | 0.0006 | 0.0297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0297
A. | Regular Establishment | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
|  | Actual Exp. | 0 | 0 | 0
B. | Work Charged Establishment | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
|  | Actual Exp. | 0 | 0 | 0 | 0
C. | Minor Works
a) | Construction of Site office building including land cost for site | Target Exp. | 0 | 0 | 0 | 0 | 0.0261 | 0.0783 | 0.1566 | 0.261 | 0.0269 | 0.0807 | 0.1614 | 0.269 | 0.0711 | 0.0711 | 0.1188 | 0.261 | 0.792 | 3 | 0
|  | Actual Exp. | 0 | 0 | 0 | 0
b) | Works for opening of New Site | Target Exp. | 0 | 0 | 0 | 0 | 0.002376 | 0.007128 | 0.014256 | 0.02376 | 0.002448 | 0.007344 | 0.014688 | 0.02448 | 0.010098 | 0.003564 | 0.003564 | 0.02376 | 0.072 | 3 | 0
|  | Actual Exp. | 0 | 0 | 0 | 0
c) | R&M of Sites | Target Exp. | 0 | 0 | 0 | 0 | 0.001188 | 0.003564 | 0.007128 | 0.01188 | 0.001224 | 0.003672 | 0.007344 | 0.01224 | 0.00324 | 0.00324 | 0.0054 | 0.01188 | 0.036 | 3 | 0
|  | Actual Exp. | 0.0011 | 0.0014 | 0.0006 | 0.0031
d) | Hiring of Watch & Ward Service | Target Exp. | 0 | 0 | 0 | 0 | 0.004752 | 0.014256 | 0.028512 | 0.04752 | 0.004896 | 0.014688 | 0.029376 | 0.04896 | 0.01296 | 0.01296 | 0.0216 | 0.04752 | 0.144 | 3 | 0
|  | Actual Exp. | 0.0166 | 0.01 | 0 | 0.0266
D. | Motor Vehicle
i) | Procurement of Inspection Vehicle | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Actual Exp. | 0 | 0 |  | 0
ii) | R&M of Motor Vehicle including salary of Driver | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Actual Exp. | 0 | 0 | 0 | 0
E. | Machinery & Equipment
a) | Purchase of High value equipment ( > 5 Lakh) | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Actual Exp. | 0 | 0 | 0 | 0
b) | Purchase of Low value equipment (< 5 Lakh) | Target Exp. | 0 | 0 | 0 | 0 | 0.011253 | 0.033759 | 0.067518 | 0.11253 | 0.011594 | 0.034782 | 0.069564 | 0.11594 | 0.03069 | 0.03069 | 0.05115 | 0.11253 | 0.341 | 3 | 0
|  | Actual Exp. | 0 | 0 | 0 | 0

## Part_B_Mahi
For the Month of June 2015. |  |  |  | Mahi Division , |  | NTBO | [8 empty] | Gandhinagar | [5 empty] | Amount in Crore
S.No | Activity | Financial Progress (INR in Crore) | Physical Progress | [15 empty] | CUMMULATIVE | Physical Target | Physical Ach. | Remarks
|  |  | Q1 |  |  |  | Q2 |  |  |  | Q3 |  |  |  | Q4
|  |  | April | May | June | Total- Q1 | July | Aug | Sep | Total- Q2 | Oct | Nov | Dec | Total- Q3 | Jan | Feb | Mar | Total- Q4
2 | Part-B: Expansion of Hydrological Observation Network by opening new Hydrological Observation sites under CWC | Target Exp. | 8.118e-05 | 0.00024354 | 0.0010217 | 0.0017028 | 0.005148 | 0.015444 | 0.030888 | 0.05148 | 0.005304 | 0.015912 | 0.031824 | 0.05304 | 0.01404 | 0.01404 | 0.0234 | 0.05148 | 0.156
|  | Actual Exp. | 0.0972 | 0.0014 | 0 | 0.0986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0986
A. | Regular Establishment | Target Exp. | 8.118e-05 | 0.00024354 | 0.00048708 | 0.0008118 | 0.001353 | 0.004059 | 0.008118 | 0.01353 | 0.001394 | 0.004182 | 0.008364 | 0.01394 | 0.00369 | 0.00369 | 0.00615 | 0.01353 | 0.041 | 0
|  | Actual Exp. | 0.0004 | 0.0014 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
B. | Work Charged Establishment | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Actual Exp. |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C. | Minor Works
a) | Construction of Site office building including land cost for site | Target Exp. | 0 | 0 | 0.0005346 | 0.000891 | 0.001485 | 0.004455 | 0.00891 | 0.01485 | 0.00153 | 0.00459 | 0.00918 | 0.0153 | 0.00405 | 0.00405 | 0.00675 | 0.01485 | 0.045 | 2 |  | Construction of site office building including land cost for sites& Construction of site office building including land cost for Snow & Met Stations
|  | Actual Exp. | [7 empty] | 0 |  |  |  | 0 |  |  |  | 0 | 0
b) | Works for opening of New Site | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
|  | Actual Exp. | [7 empty] | 0
c) | R&M of Sites | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
|  | Actual Exp. | [7 empty] | 0 |  |  |  | 0 |  |  |  | 0 | 0
d) | Hiring of Watch & Ward Service | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Actual Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D. | Motor Vehicle
i) | Procurement of Inspection Vehicle | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Actual Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ii) | R&M of Motor Vehicle including salary of Driver | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Actual Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E. | Machinery & Equipment
a) | Purchase of High value equipment ( > 5 Lakh) | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2
|  | Actual Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
b) | Purchase of Low value equipment (< 5 Lakh) | Target Exp. | 0 | 0 | 0 | 0 | 0.00231 | 0.00693 | 0.01386 | 0.0231 | 0.00238 | 0.00714 | 0.01428 | 0.0238 | 0.0063 | 0.0063 | 0.0105 | 0.0231 | 0.07 |  |  | outstanding payment
|  | Actual Exp. | 0.0968 | 0 |  | 0.0968 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0.0968

## combined part C
WORK PLAN OF MOWR FOR THE F.Y. 2015-16
Development of Water Resources Information System (DWRIS) Plan Scheme
Progress of Upgradation of Water Quality Laboratory for Monitoring of Water Quality at existing and New Station under CWC
For the Month of June 15 |  |  |  | Combined status of Mahi Division and Tapi Division under NTBO Gandhinagar | [13 empty] | Amount in Crore |  |  | Amount in Crore
S.No | Activity | Financial Progress (INR in Crore) | Financial Progress | [15 empty] | CUMMULATIVE | Physical Target | Physical Ach. | Remarks Tapi division Surat | Remarks Mahi division Gandhinagar
|  |  | Q1 |  |  |  | Q2 |  |  |  | Q3 |  |  |  | Q4
|  |  | April | May | June | Total- Q1 | July | Aug | Sep | Total- Q2 | Oct | Nov | Dec | Total- Q3 | Jan | Feb | Mar | Total- Q4
3 | PART-C: Upgradation of Water Quality Laboratory for Monitoring of Water Quality at existing and New Station under CWC | Target Exp. | 0.007104 | 0.021312 | 0.042624 | 0.07104 | 0.0078144 | 0.023443 | 0.046886 | 0.078144 | 0.00888 | 0.02664 | 0.05328 | 0.0888 | 0.031968 | 0.031968 | 0.05328 | 0.11722 | 0.3552 | #REF! | #REF!
|  | Actual Exp. | 0.0133 | 0.0191 | 0.0214 | 0.0538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0538 | #REF! | 0
A. | Regular Establishment | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | 0
|  | Actual Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF!
B. | Work Charged Establishment | Target Exp. | 0.00072 | 0.00216 | 0.00432 | 0.0072 | 0.000792 | 0.002376 | 0.004752 | 0.00792 | 0.0009 | 0.0027 | 0.0054 | 0.009 | 0.00324 | 0.00324 | 0.0054 | 0.01188 | 0.036 | #REF! | 0 | #REF! | #REF!
|  | Actual Exp. | 0.0028 | 0.0014 | 0.0014 | 0.0056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF!
C. | Outsourcing of JRF | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | 0
|  | Actual Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF!
D. | Minor Works
a) | Procurement of Consumabales | Target Exp. | 0.0007 | 0.0021 | 0.0042 | 0.007 | 0.00077 | 0.00231 | 0.00462 | 0.0077 | 0.000875 | 0.002625 | 0.00525 | 0.00875 | 0.00315 | 0.00315 | 0.00525 | 0.01155 | 0.035 | LS | LS | #REF! | #REF!
|  | Actual Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF!
b) | AMC of Lab Equipment | Target Exp. | 0.0002 | 0.0006 | 0.0012 | 0.002 | 0.00022 | 0.00066 | 0.00132 | 0.0022 | 0.00025 | 0.00075 | 0.0015 | 0.0025 | 0.0009 | 0.0009 | 0.0015 | 0.0033 | 0.01 | #REF! | 0 | #REF! | #REF!
|  | Actual Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF!
c) | Renovation of Laboratory | Target Exp. | 0.0014 | 0.0042 | 0.0084 | 0.014 | 0.00154 | 0.00462 | 0.00924 | 0.0154 | 0.00175 | 0.00525 | 0.0105 | 0.0175 | 0.0063 | 0.0063 | 0.0105 | 0.0231 | 0.07 | 2 | 0 | #REF! | #REF!
|  | Actual Exp. | 0 | 0 | 0.015 | 0.015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF!
d) | R&M of Water Qulaity Sites | Target Exp. | 0.00066 | 0.00198 | 0.00396 | 0.0066 | 0.000726 | 0.002178 | 0.004356 | 0.00726 | 0.000825 | 0.002475 | 0.00495 | 0.00825 | 0.00297 | 0.00297 | 0.00495 | 0.01089 | 0.033 | #REF! | 11 | #REF! | #REF!
|  | Actual Exp. | 0.0036 | 0.0056 | 0.0004 | 0.0096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF!
e) | Outsourcing of Vehicle | Target Exp. | 0.00096 | 0.00288 | 0.00576 | 0.0096 | 0.001056 | 0.003168 | 0.006336 | 0.01056 | 0.0012 | 0.0036 | 0.0072 | 0.012 | 0.00432 | 0.00432 | 0.0072 | 0.01584 | 0.048 | #REF! | 1 | #REF! | #REF!
|  | Actual Exp. | 0.005 | 0.0085 | 0 | 0.0135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF!
f) | Out sourcing of DEO, MTS services | Target Exp. | 0.000864 | 0.002592 | 0.005184 | 0.00864 | 0.0009504 | 0.0028512 | 0.0057024 | 0.009504 | 0.00108 | 0.00324 | 0.00648 | 0.0108 | 0.003888 | 0.003888 | 0.00648 | 0.014256 | 0.0432 | #REF! | 0 | #REF! | #REF!
|  | Actual Exp. | 0.0019 | 0.0015 | 0 | 0.0034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF!
E. | Machinery & Equipment
a) | Purchase of High value equipment ( > 5 Lakh) | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | 0 | #REF! | #REF!
|  | Actual Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF!
b) | Purchase of Low value equipment (< 5 Lakh) | Target Exp. | 0.0016 | 0.0048 | 0.0096 | 0.016 | 0.00176 | 0.00528 | 0.01056 | 0.0176 | 0.002 | 0.006 | 0.012 | 0.02 | 0.0072 | 0.0072 | 0.012 | 0.0264 | 0.08 | #REF! | 0 | #REF! | #REF!
|  | Actual Exp. | 0 | 0.0021 | 0.0046 | 0.0067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF!

## Part_C_Tapi
WORK PLAN OF MOWR FOR THE F.Y. 2015-16
Development of Water Resources Information System (DWRIS) Plan Scheme
Progress of Upgradation of Water Quality Laboratory for Monitoring of Water Quality at existing and New Station under Tapi division, CWC, Surat.
For the Month of June 2015 | [5 empty] | Tapi Division | [11 empty] | Amount in crore
S.No | Activity | Financial Progress (INR in Crore) | Physical Progress | [15 empty] | CUMMULATIVE | Physical Target | Physical Ach.
|  |  | Q1 |  |  |  | Q2 |  |  |  | Q3 |  |  |  | Q4
|  |  | April | May | June | Total- Q1 | July | Aug | Sep | Total- Q2 | Oct | Nov | Dec | Total- Q3 | Jan | Feb | Mar | Total- Q4
3 | PART-C: Upgradation of Water Quality Laboratory for Monitoring of Water Quality at existing and New Station under CWC | Target Expenditure | 0.005804 | 0.017412 | 0.034824 | 0.05804 | 0.0063844 | 0.019153 | 0.038306 | 0.063844 | 0.007255 | 0.021765 | 0.04353 | 0.07255 | 0.026118 | 0.026118 | 0.04353 | 0.095766 | 0.2902
|  | Actual Expenditure | 0.0133 | 0.0191 | 0.0018 | 0.0342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0342
A. | Regular Establishment | Target Expenditure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Actual Expenditure | 0 | 0 | 0 | 0
B. | Work Charged Establishment | Target Expenditure | 0.00072 | 0.00216 | 0.00432 | 0.0072 | 0.000792 | 0.002376 | 0.004752 | 0.00792 | 0.0009 | 0.0027 | 0.0054 | 0.009 | 0.00324 | 0.00324 | 0.0054 | 0.01188 | 0.036 | 1
|  | Actual Expenditure | 0.0028 | 0.0014 | 0.0014 | 0.0056
C. | Outsourcing of JRF | Target Expenditure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Actual Expenditure | 0 | 0 | 0 | 0
D. | Minor Works
a) | Procurement of Consumabales | Target Exp. | 0.0002 | 0.0006 | 0.0012 | 0.002 | 0.00022 | 0.00066 | 0.00132 | 0.0022 | 0.00025 | 0.00075 | 0.0015 | 0.0025 | 0.0009 | 0.0009 | 0.0015 | 0.0033 | 0.01 | LS
|  | Actual Exp. | 0 | 0 | 0 | 0
b) | AMC of Lab Equipment | Target Exp. | 0.0002 | 0.0006 | 0.0012 | 0.002 | 0.00022 | 0.00066 | 0.00132 | 0.0022 | 0.00025 | 0.00075 | 0.0015 | 0.0025 | 0.0009 | 0.0009 | 0.0015 | 0.0033 | 0.01
|  | Actual Exp. | 0 | 0 | 0 | 0
c) | Renovation of Laboratory | Target Exp. | 0.001 | 0.003 | 0.006 | 0.01 | 0.0011 | 0.0033 | 0.0066 | 0.011 | 0.00125 | 0.00375 | 0.0075 | 0.0125 | 0.0045 | 0.0045 | 0.0075 | 0.0165 | 0.05 | 1
|  | Actual Exp. | 0 | 0 | 0 | 0
d) | R&M of Water Qulaity Sites | Target Exp. | 0.00066 | 0.00198 | 0.00396 | 0.0066 | 0.000726 | 0.002178 | 0.004356 | 0.00726 | 0.000825 | 0.002475 | 0.00495 | 0.00825 | 0.00297 | 0.00297 | 0.00495 | 0.01089 | 0.033 | 11 | 11
|  | Actual Exp. | 0.0036 | 0.0056 | 0.0004 | 0.0096
e) | Outsourcing of Vehicle | Target Exp. | 0.00096 | 0.00288 | 0.00576 | 0.0096 | 0.001056 | 0.003168 | 0.006336 | 0.01056 | 0.0012 | 0.0036 | 0.0072 | 0.012 | 0.00432 | 0.00432 | 0.0072 | 0.01584 | 0.048 | 1 | 1
|  | Actual Exp. | 0.005 | 0.0085 | 0 | 0.0135
f) | Out sourcing of DEO, MTS services | Target Exp. | 0.000864 | 0.002592 | 0.005184 | 0.00864 | 0.0009504 | 0.0028512 | 0.0057024 | 0.009504 | 0.00108 | 0.00324 | 0.00648 | 0.0108 | 0.003888 | 0.003888 | 0.00648 | 0.014256 | 0.0432 | 2
|  | Actual Exp. | 0.0019 | 0.0015 | 0 | 0.0034
E. | Machinery & Equipment
a) | Purchase of High value equipment ( > 5 Lakh) | Target Exp. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Actual Exp. | 0 | 0 | 0 | 0
b) | Purchase of Low value equipment (< 5 Lakh) | Target Exp. | 0.0012 | 0.0036 | 0.0072 | 0.012 | 0.00132 | 0.00396 | 0.00792 | 0.0132 | 0.0015 | 0.0045 | 0.009 | 0.015 | 0.0054 | 0.0054 | 0.009 | 0.0198 | 0.06
|  | Actual Exp. | 0 | 0.0021 | 0 | 0.0021

## Part_C_Mahi
WORK PLAN OF MOWR FOR THE F.Y. 2014-15
Development of Water Resources Information System (DWRIS) Plan Scheme
Progress of Upgradation of Water Quality Laboratory for Monitoring of Water Quality at existing and New Station under CWC
For the Month of June 2015. |  |  |  | Mahi Division , |  | NTBO | [8 empty] | Gandhinagar | [5 empty] | Amount in Crore
S.No | Activity | Financial Progress (INR in Crore) | Physical Progress | [15 empty] | CUMMULATIVE | Physical Target | Physical Ach. | Remarks
|  |  | Q1 |  |  |  | Q2 |  |  |  | Q3 |  |  |  | Q4
|  |  | April | May | June | Total- Q1 | July | Aug | Sep | Total- Q2 | Oct | Nov | Dec | Total- Q3 | Jan | Feb | Mar | Total- Q4
3 | PART-C: Upgradation of Water Quality Laboratory for Monitoring of Water Quality at existing and New Station under CWC | Target Expenditure | 0.0013 | 0.0039 | 0.0078 | 0.013 | 0.00143 | 0.00429 | 0.00858 | 0.0143 | 0.001625 | 0.004875 | 0.00975 | 0.01625 | 0.00585 | 0.00585 | 0.00975 | 0.02145 | 0.065
|  | Actual Expenditure | 0 | 0 | 0.0196 | 0.0196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0196
A. | Regular Establishment | Target Expenditure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Actual Expenditure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. | Work Charged Establishment | Target Expenditure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Actual Expenditure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C. | Outsourcing of JRF | Target Expenditure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Actual Expenditure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D. | Minor Works
a) | Procurement of Consumabales | Target Expenditure | 0.0005 | 0.0015 | 0.003 | 0.005 | 0.00055 | 0.00165 | 0.0033 | 0.0055 | 0.000625 | 0.001875 | 0.00375 | 0.00625 | 0.00225 | 0.00225 | 0.00375 | 0.00825 | 0.025 | LS | LS | Chemical (Imported & Indian) for Analysis of Chemical & Biological parameters ,Chemical and Reference solutions for Ion Meter/ AAS/GC, Gases, Solvent, Electrode for Ion Meter - 2 per lab, Electrode for Auto titrator ,Electrode for Conductivity meter, pH meter, DO meter, Glass Wares, General / Computer stationary, Batteries for UPS
|  | Actual Expenditure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
b) | AMC of Lab Equipment | Target Expenditure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Not required for this year
|  | Actual Expenditure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
c) | Renovation of Laboratory | Target Expenditure | 0.0004 | 0.0012 | 0.0024 | 0.004 | 0.00044 | 0.00132 | 0.00264 | 0.0044 | 0.0005 | 0.0015 | 0.003 | 0.005 | 0.0018 | 0.0018 | 0.003 | 0.0066 | 0.02 | 1
|  | Actual Expenditure | 0 | 0 | 0.015 | 0.015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
d) | R&M of Water Qulaity Sites | Target Expenditure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 11 | 11
|  | Actual Expenditure | [7 empty] | 0 |  |  |  | 0 |  |  |  | 0 | 0
e) | Outsourcing of Vehicle | Target Expenditure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Actual Expenditure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
f) | Out sourcing of DEO, MTS services | Target Expenditure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2
|  | Actual Expenditure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E. | Machinery & Equipment
a) | Purchase of High value equipment ( > 5 Lakh) | Target Expenditure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Actual Expenditure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
b) | Purchase of Low value equipment (< 5 Lakh) | Target Expenditure | 0.0004 | 0.0012 | 0.0024 | 0.004 | 0.00044 | 0.00132 | 0.00264 | 0.0044 | 0.0005 | 0.0015 | 0.003 | 0.005 | 0.0018 | 0.0018 | 0.003 | 0.0066 | 0.02 |  |  | Misc. Lab Equipment
|  | Actual Expenditure | 0 | 0 | 0.0046 | 0.0046 | 0 |  | 0 | [5 empty] | 0